## Dashboard
UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard
UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard | UOB Agreement UAT & Release Dashboard
Release gate: all required UAT cases pass, no open Critical/High defects, and every required release checkpoint is complete. | Release gate: all required UAT cases pass, no open Critical/High defects, and every required release checkpoint is complete. | Release gate: all required UAT cases pass, no open Critical/High defects, and every required release checkpoint is complete. | Release gate: all required UAT cases pass, no open Critical/High defects, and every required release checkpoint is complete. | Release gate: all required UAT cases pass, no open Critical/High defects, and every required release checkpoint is complete. | Release gate: all required UAT cases pass, no open Critical/High defects, and every required release checkpoint is complete. | Release gate: all required UAT cases pass, no open Critical/High defects, and every required release checkpoint is complete. | Release gate: all required UAT cases pass, no open Critical/High defects, and every required release checkpoint is complete.
UAT metric | Result |  | Release candidate identification | Release candidate identification | Release candidate identification | Release candidate identification | Release candidate identification
Total UAT cases | 36 |  | Release name/version
Required P0/P1 cases | 36 |  | Git commit
Required cases passed | 0 |  | Git tag
Failed cases | 0 |  | UAT environment
Blocked cases | 0 |  | UAT start
Executed cases | 0 |  | UAT end
Completion | 0% |  | Planned production window
Open Critical defects | 0
Open High defects | 0 |  | Scope boundary | Scope boundary | Scope boundary | Scope boundary | Scope boundary
Release gate | NOT READY |  | Included | Agreement module: approval, lifecycle, signing/status, performance, public catalogue
|  |  | Excluded | Initiative module
|  |  | Excluded | Notification and escalation module
|  |  | Retained | Legacy Agreement compatibility boundary until Initiative relationship migration
Start on UAT only after the full automated suite reports 28 passed and 0 failed on the exact candidate commit. | Start on UAT only after the full automated suite reports 28 passed and 0 failed on the exact candidate commit. | Start on UAT only after the full automated suite reports 28 passed and 0 failed on the exact candidate commit. | Start on UAT only after the full automated suite reports 28 passed and 0 failed on the exact candidate commit. | Start on UAT only after the full automated suite reports 28 passed and 0 failed on the exact candidate commit. | Start on UAT only after the full automated suite reports 28 passed and 0 failed on the exact candidate commit. | Start on UAT only after the full automated suite reports 28 passed and 0 failed on the exact candidate commit. | Start on UAT only after the full automated suite reports 28 passed and 0 failed on the exact candidate commit.

## UAT Cases
Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases
Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases | Agreement User-Acceptance Test Cases
Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID. | Complete Actual Result, Status, Evidence, Tester, and Test Date. Link every failure to a Defect ID.
Test ID | Area | Priority | Role | Preconditions | Test steps | Expected result | Actual result | Status | Defect ID | Evidence reference | Tester | Test date | Notes
UAT-001 | Access & sessions | P0 | All roles | UAT accounts are active; use separate browser profiles or isolated tabs. | Sign in as Dean and VP in separate contexts; switch repeatedly; refresh both registers and detail pages. | Each context keeps its own identity. No cached draft, document, or task from the other actor appears. |  | Not Run
UAT-002 | Access & sessions | P0 | Dean / VP | Dean owns a DRAFT Agreement. | Open the draft as Dean. Copy its URL and open it as VP. Also change the numeric ID to another private draft. | Dean can open the draft; VP receives not found and sees no metadata, versions, or documents. |  | Not Run
UAT-003 | Document security | P0 | Dean / reviewer | A secure document is attached to an Agreement under review. | Download while assigned; complete the review; reuse the same download URL after handoff. | Download works only during active authorized access. The former reviewer receives not found after handoff. |  | Not Run
UAT-004 | Legacy boundary | P1 | Administrator | Workspace replacement switch is enabled. | Open each retired Agreement admin add/list/review/edit route while signed in and signed out. | Routes redirect to the canonical workspace; signed-out users reach login with a safe return target. Initiative pages are unchanged. |  | Not Run
UAT-005 | Agreement CRUD | P0 | Dean | At least one active partner exists. | Create a complete Agreement with dates, justification, expected value, objectives, collaboration areas, implementation methods, partner, and representative structured fields. | Agreement is DRAFT; all saved values render correctly; partner link, version 1, and audit entry exist. |  | Not Run
UAT-006 | Agreement CRUD | P0 | Dean | Create form is open. | Attempt submission with required title, type, description, partner, and one additional required submission field missing. | Field-specific validation appears; no partial Agreement/workflow data is committed. |  | Not Run
UAT-007 | Versions | P1 | Dean | A DRAFT Agreement exists. | Edit the title or description with a change summary; open version history and compare versions 1 and 2. | Version number increments; the earlier snapshot is unchanged; latest details show the edit. |  | Not Run
UAT-008 | Document security | P0 | Dean | An editable DRAFT exists; test PDF/DOC/DOCX files are available. | Upload a valid file, inspect metadata, download it, then try a renamed executable or file over 10 MB. | Valid file is private and checksum-linked to the current version; invalid upload is rejected without residue; no storage path is exposed. |  | Not Run
UAT-009 | Submission | P0 | Dean | The Agreement is complete and linked to an active partner. | Submit the Agreement once, then attempt a second submission. | Status becomes UNDER_REVIEW; VP_INITIAL is active exactly once; duplicate submission is rejected. |  | Not Run
UAT-010 | Initial VP | P0 | Vice President | VP has the active initial-review assignment. | Open the VP task, review the latest Agreement/version, select both Legal and Finance, and approve initial routing. | VP_INITIAL completes; Legal and Finance become active in parallel with one assignment each. |  | Not Run
UAT-011 | Specialist review | P0 | Finance reviewer | Legal and Finance are both active. | Approve Finance before Legal; inspect the VP inbox. | Finance completes and leaves its inbox; Final VP remains pending until Legal completes. |  | Not Run
UAT-012 | Specialist review | P0 | Legal reviewer | Finance is approved and Legal is active. | Approve Legal and inspect Legal, Finance, and VP inboxes. | Legal completes; Final VP activates exactly once; completed specialist tasks disappear. |  | Not Run
UAT-013 | Final VP | P0 | Vice President | All required specialists are approved. | Open Final VP task, verify Legal/Finance outcomes, and approve recommendation. | Final VP completes; President approval activates with one President assignment. |  | Not Run
UAT-014 | President & publication | P0 | President | President has the active final assignment. | Approve the Agreement; reopen task URL; open the public catalogue and the generated public reference. | Workflow is COMPLETED; Agreement is APPROVED; duplicate decision is rejected; allow-listed public details appear without private workflow/data. |  | Not Run
UAT-015 | Change request | P0 | Legal reviewer | A second Agreement has active Legal and Finance review. | Request changes from Legal with a reason while Finance is active. | Legal becomes CHANGES_REQUESTED; Finance pauses; VP mediation activates with the exact recorded reason. |  | Not Run
UAT-016 | VP mediation | P0 | Vice President | VP mediation is active for UAT-015. | Route the Agreement to the creator and inspect assignments/status. | Creator redraft becomes active; Agreement becomes REVISION_REQUIRED; obsolete reviewer assignments are inactive; baseline version is stored. |  | Not Run
UAT-017 | Redraft | P0 | Dean | Creator redraft is active. | Try resubmitting before an edit; then edit with a change summary and resubmit. | First resubmission is rejected; edit creates a newer immutable version; valid resubmission starts a new review cycle at Initial VP. |  | Not Run
UAT-018 | VP mediation | P1 | Vice President | A specialist change request is awaiting VP mediation. | Route once to Legal or Finance rather than the creator; inspect task ownership. | Only the selected specialist step reactivates with a new assignment; unrelated assignments remain inactive. |  | Not Run
UAT-019 | President change | P0 | President / VP | A separate Agreement reaches President review. | President requests changes with a reason; VP opens mediation and routes to creator or specialist. | President task closes; Final VP decision is cleared; VP receives the recorded reason and controls the next route. |  | Not Run
UAT-020 | Rejection | P0 | VP or President | A disposable Agreement has an active decision task. | Attempt rejection without a reason, then reject with confirmation and a reason; repeat the decision. | Blank reason is rejected; valid rejection makes workflow and Agreement terminally REJECTED; no active assignment or duplicate history remains. |  | Not Run
UAT-021 | Renewal | P1 | Creator and approvers | An APPROVED or ACTIVE source Agreement exists. | Create a renewal with proposed dates and evidence; complete the full lifecycle approval route. | One APPROVED successor is created with the proposed dates; source is unchanged; RENEWAL lineage and immutable provenance are visible. |  | Not Run
UAT-022 | Amendment | P1 | Creator and approvers | An APPROVED or ACTIVE source Agreement exists. | Create an amendment with exact clauses and private evidence; approve it through President. | One APPROVED cloned successor is created; approved clauses remain authoritative in the lifecycle request; AMENDMENT lineage is visible. |  | Not Run
UAT-023 | Termination | P1 | Creator and approvers | An APPROVED or ACTIVE disposable source exists. | Create and approve a termination request. | Source becomes TERMINATED with action history; no successor is created; terminated record is not publicly listed. |  | Not Run
UAT-024 | Lifecycle documents | P0 | Requester / reviewers | A lifecycle draft has a private attachment. | Submit it; verify requester becomes read-only; test access at VP, then route to Legal and retry as former VP. | Document follows only the requester and exact active reviewer; VP access ends immediately after handoff; no storage path is disclosed. |  | Not Run
UAT-025 | Signing | P0 | Agreement creator | An APPROVED Agreement and secure SIGNED_AGREEMENT document exist. | Enter signing/effective/expiry dates and at least one UOB and one partner signatory; finalize with effective date today. | One immutable signing record is created; signatories freeze; Agreement becomes ACTIVE; referenced document cannot be deleted. |  | Not Run
UAT-026 | Activation | P1 | Creator / administrator | An APPROVED Agreement is finalized with a future effective date. | Confirm it remains scheduled; preview status sync; run commit with --as-of on effective date. | Preview writes nothing; commit changes status to ACTIVE once and creates one status/audit event. |  | Not Run
UAT-027 | Expiry | P1 | Administrator | An ACTIVE Agreement has an expiry date before the controlled as-of date. | Run operational sync twice for the day after expiry. | First run makes it EXPIRED; second run is idempotent with no duplicate event; TERMINATED records remain unchanged. |  | Not Run
UAT-028 | Signing security | P0 | Creator / administrator | A signed document is referenced by a finalized signing record. | Attempt document deletion and attempt a second signing finalization. | Both operations are rejected; original document, signing record, and status remain unchanged. |  | Not Run
UAT-029 | Reporting periods | P1 | Administrator | An eligible ACTIVE/EXPIRED Agreement requires annual reporting. | Run period generator in preview, commit it twice, and open the generated report. | Preview writes nothing; first commit creates one current period with copied baselines; second commit creates no duplicate. |  | Not Run
UAT-030 | Performance report | P1 | Agreement creator | A generated report is editable and secure ANNUAL_REPORT evidence exists. | Enter summary, achievements, every actual metric, program progress, and evidence; submit. | Complete report becomes SUBMITTED; missing required data or invalid evidence is rejected; approved Agreement targets remain unchanged. |  | Not Run
UAT-031 | Performance return | P1 | Report reviewer / creator | A report is SUBMITTED; reviewer is not the preparer. | Try returning without comments; return with comments; creator edits and resubmits. | Blank return is rejected; valid return reopens editing with comments; resubmission returns it to SUBMITTED with event history. |  | Not Run
UAT-032 | Performance acceptance | P0 | Report reviewer | A complete report is resubmitted; reviewer differs from preparer. | Accept the report; attempt an owner edit and evidence deletion afterward. | Report becomes immutable ACCEPTED; edit and linked-document deletion are rejected; self-review remains prohibited. |  | Not Run
UAT-033 | Management dashboard | P1 | Agreement approver | Accepted and non-accepted reports exist for the selected year. | Open dashboard as creator without permission and as approver; compare aggregate totals with report states. | Creator is forbidden; approver sees deadlines and counts; KPI/program totals include ACCEPTED reports only and expose no narratives/documents. |  | Not Run
UAT-034 | Public catalogue | P0 | Public visitor | Records exist in DRAFT, UNDER_REVIEW, APPROVED, ACTIVE, EXPIRED, REJECTED, and TERMINATED states. | Search catalogue and open public detail/page source for representative records. | Only APPROVED and ACTIVE records appear; private identities, comments, versions, audits, documents, storage data, and lifecycle provenance are absent. |  | Not Run
UAT-035 | Historical import | P1 | Administrator | Controlled 41-row import has been completed in this environment. | Run read-only import verification; inspect one imported version/audit/public record and confirm no workflow exists. | Exactly 41 controlled records verify; each has one immutable version/audit, no active workflow, and only allow-listed public data. |  | Not Run
UAT-036 | Release security | P0 | Technical lead | Candidate commit is deployed and readiness passes. | Inspect Network for X-Request-Id and X-UOB-Tab-Session; send malformed JSON, wrong content type, array JSON, oversized JSON, and a mutation without tab-session header in UAT. | Requests receive controlled 422/415/413/400 responses as applicable; no mutation occurs; private paths and credentials are absent. |  | Not Run

## Defects
Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log
Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log | Agreement UAT Defect Log
Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit. | Critical and High defects block release. Every fixed defect requires case retest and the full automated suite on the new commit.
Defect ID | UAT Case | Summary | Severity | Status | Owner | Date raised | Target fix | Retest status | Evidence | Workaround / deferral | Resolution | Notes

## Release Checklist
Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist
Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist | Agreement Release Checklist
Complete every row before release closure. P0 rows cannot be deferred without rejecting the release gate. | Complete every row before release closure. P0 rows cannot be deferred without rejecting the release gate. | Complete every row before release closure. P0 rows cannot be deferred without rejecting the release gate. | Complete every row before release closure. P0 rows cannot be deferred without rejecting the release gate. | Complete every row before release closure. P0 rows cannot be deferred without rejecting the release gate. | Complete every row before release closure. P0 rows cannot be deferred without rejecting the release gate. | Complete every row before release closure. P0 rows cannot be deferred without rejecting the release gate. | Complete every row before release closure. P0 rows cannot be deferred without rejecting the release gate.
Phase | Checkpoint | Owner | Priority | Required evidence | Status | Evidence reference | Notes
Pre-UAT | Record exact Git commit and confirm working tree scope | Technical lead | P0 | Commit hash and clean-status capture | Not Started
Pre-UAT | Confirm full automated suite is 28 passed / 0 failed | Technical lead | P0 | Complete console output | Not Started
Pre-UAT | Confirm readiness test passes | Technical lead | P0 | Readiness output | Not Started
Pre-UAT | Create and verify UAT database backup | DB administrator | P0 | Backup path, size, pg_restore --list | Not Started
Pre-UAT | Assign UAT actors and witnesses | Test lead | P1 | Completed Sign-off and Accounts sheets | Not Started
Pre-UAT | Confirm Initiative and notification work are excluded | Project owner | P0 | Approved scope record | Not Started
UAT | Complete all P0 UAT cases | Test lead | P0 | UAT Cases sheet and evidence | Not Started
UAT | Complete all P1 UAT cases | Test lead | P1 | UAT Cases sheet and evidence | Not Started
UAT | Resolve or approve deferral for every defect | Project owner | P0 | Defects sheet | Not Started
UAT | Re-run full automated suite after final defect fix | Technical lead | P0 | 28/28 output on final commit | Not Started
Recovery | Rehearse database restore to a disposable database | DB administrator | P0 | Restore command and verification | Not Started
Recovery | Verify private-document backup and matching restore point | Technical lead | P0 | File inventory/checksum evidence | Not Started
Recovery | Confirm rollback owner and decision authority | Release manager | P0 | Named owner in sign-off | Not Started
Release | Approve release candidate commit/tag | Project owner | P0 | Signed decision | Not Started
Release | Verify local database secret and private files are not staged | Technical lead | P0 | git check-ignore and staged-file list | Not Started
Release | Pause Agreement scheduled jobs | Release operator | P1 | Task Scheduler status | Not Started
Release | Take and verify fresh production backups | DB administrator | P0 | Database and private-file backup evidence | Not Started
Release | Deploy exact approved commit and pending migrations only | Release operator | P0 | Deployment/migration log | Not Started
Post-release | Run read-only production readiness test | Technical lead | P0 | Passing readiness output | Not Started
Post-release | Complete focused authorized browser smoke checks | Test lead | P0 | Screenshots/results | Not Started
Post-release | Verify public allow-list and private document protection | Security witness | P0 | Public/private access evidence | Not Started
Post-release | Resume and manually verify both Agreement scheduled jobs | Release operator | P1 | Job output and scheduler status | Not Started
Post-release | Record production decision and observation result | Release manager | P1 | Completed sign-off/closure | Not Started

## Sign-off
Agreement Release Sign-off | Agreement Release Sign-off | Agreement Release Sign-off | Agreement Release Sign-off | Agreement Release Sign-off
Agreement Release Sign-off | Agreement Release Sign-off | Agreement Release Sign-off | Agreement Release Sign-off | Agreement Release Sign-off
Decision options: Approved, Approved with conditions, Rejected. Pending is not a release approval. | Decision options: Approved, Approved with conditions, Rejected. Pending is not a release approval. | Decision options: Approved, Approved with conditions, Rejected. Pending is not a release approval. | Decision options: Approved, Approved with conditions, Rejected. Pending is not a release approval. | Decision options: Approved, Approved with conditions, Rejected. Pending is not a release approval.
Responsibility | Name | Decision | Date | Comments / conditions
Agreement process owner |  | Pending
Vice President Office representative |  | Pending
Legal Office representative |  | Pending
Finance Office representative |  | Pending
President Office representative |  | Pending
Technical lead / release manager |  | Pending
Final release decision | Pending
Decision date
Release manager
Rollback owner
Conditions / rejection reason
Observation period result

## Environment & Accounts
UAT Environment & Development Accounts | UAT Environment & Development Accounts | UAT Environment & Development Accounts | UAT Environment & Development Accounts | UAT Environment & Development Accounts | UAT Environment & Development Accounts
UAT Environment & Development Accounts | UAT Environment & Development Accounts | UAT Environment & Development Accounts | UAT Environment & Development Accounts | UAT Environment & Development Accounts | UAT Environment & Development Accounts
Never record passwords in this workbook. Development credentials are defined in seed_dev.sql and must never be used in production. | Never record passwords in this workbook. Development credentials are defined in seed_dev.sql and must never be used in production. | Never record passwords in this workbook. Development credentials are defined in seed_dev.sql and must never be used in production. | Never record passwords in this workbook. Development credentials are defined in seed_dev.sql and must never be used in production. | Never record passwords in this workbook. Development credentials are defined in seed_dev.sql and must never be used in production. | Never record passwords in this workbook. Development credentials are defined in seed_dev.sql and must never be used in production.
Environment field | Value
Environment name
Base URL
Database name
Git commit
Git tag
PHP version
PostgreSQL version
Apache/XAMPP version
Browser/version
Timezone | Asia/Bahrain
Actor | Development email | Role | Unit | UAT responsibility | Assigned tester
System administrator | dev.admin@uob.test | System Administrator | UOB | Readiness, support, controlled recovery
President | dev.president@uob.test | Agreement Creator + Approver | PRES | Final decisions
Vice President | dev.vp@uob.test | Agreement Creator + Approver | VP | Initial review, mediation, final review
Dean | dev.dean@uob.test | Agreement Creator | CIT | Create, submit, redraft, sign, report
Legal reviewer | dev.legal@uob.test | Agreement Approver | LEGAL | Legal review
Finance reviewer | dev.finance@uob.test | Agreement Approver | FIN | Optional Finance review